NHA EDUTECH

System Monitoring & Operations Guide

Career Spotlight Day  ·  Sports Day Scoring System

Version 1.0  ·  June 2026  ·  St James' Catholic High School

# 1. Quick Reference

Everything you need at a glance for both systems:

|  | Career Spotlight Day | Sports Day Scoring System |
| --- | --- | --- |
| Live URL | careerday.nhaedutech.co.uk | sportsday.nhaedutech.co.uk |
| Staff login | /staff/login | /login (Admin tab) |
| Hosting | Render.com (Frankfurt) | Render.com (Frankfurt) |
| Database | Render PostgreSQL | Supabase PostgreSQL (Ireland) |
| Uptime monitoring | UptimeRobot — every 5 mins | UptimeRobot — every 5 mins |
| GitHub repo | nhaedutech/STJ_career-spotlight-day | nhaedutech/STJ_sports-day |
| NHA EduTech support | nexthorizon@nhaedutech.co.uk · nhaedutech.co.uk |  |

# 2. Technical Monitoring

## 2.1 UptimeRobot — Automated Uptime Monitoring

Both applications are monitored 24/7 by UptimeRobot, which pings each app every 5 minutes. If an app goes down, UptimeRobot sends an automatic email alert.

| Monitor 1 | Career Spotlight Day — careerday.nhaedutech.co.uk |
| --- | --- |
| Monitor 2 | Sports Day Scoring System — sportsday.nhaedutech.co.uk |
| Check interval | Every 5 minutes |
| Alert method | Email to personal Gmail account |
| Dashboard | dashboard.uptimerobot.com |
| Free tier limit | 50 monitors — currently using 2 |

Why UptimeRobot is needed:

- Render's free tier spins down apps after 15 minutes of inactivity

- UptimeRobot pings keep both apps awake permanently at no cost

- Without it, the first visitor after a period of inactivity would wait 50+ seconds for the app to wake up

## 2.2 Render Dashboard — Logs & Deployments

The Render dashboard provides real-time logs, deployment history, and service status for both apps.

| Dashboard URL | dashboard.render.com |
| --- | --- |
| Account | nhaedutech GitHub account |
| Career Day service | stj-career-spotlight-day |
| Sports Day service | stj-sports-day |
| Log retention | Last 100 lines visible in real time |
| Auto-deploy | Triggered on every git push to main branch |

### How to check logs on Render:

- Go to dashboard.render.com

- Click on the service (stj-career-spotlight-day or stj-sports-day)

- Click Logs in the left sidebar

- Filter by time or search for specific error keywords

### Common log messages to watch for:

| Log message | What it means |
| --- | --- |
| Your service is live 🎉 | App deployed successfully and running |
| Exited with status 1 | App crashed — check logs above for the error |
| Service spinning down | Normal — UptimeRobot will wake it back up within 5 mins |
| Build failed | Code error or missing dependency — check requirements.txt |
| GET / HTTP/1.1 200 | Successful page request — app is responding normally |
| 500 Internal Server Error | App error — check logs for traceback and contact NHA EduTech |

## 2.3 Environment Variables — Critical Settings

Both apps depend on environment variables set in the Render dashboard. If these are missing or incorrect, the app will fail to start.

### Career Spotlight Day — Required Variables:

| SECRET_KEY | Flask session encryption key — must be set |
| --- | --- |
| DATABASE_URL | Render PostgreSQL internal connection URL |
| STAFF_PASSWORD | Password for careers coordinator login |
| TUTOR_PASSWORD | Shared password for form tutor login |
| PYTHON_VERSION | 3.11.0 |

### Sports Day Scoring System — Required Variables:

| SECRET_KEY | Flask session encryption key — must be set |
| --- | --- |
| DATABASE_URL | Supabase PostgreSQL transaction pooler URL |
| ADMIN_PASSWORD | Password for PE coordinator admin login |
| VOLUNTEER_PIN | PIN shared with volunteer teachers |
| RENDER | Set to: true |
| PYTHON_VERSION | 3.11.0 |

Never share environment variable values via email or chat. Store them securely in a password manager. If credentials are compromised, update them immediately in the Render dashboard.

## 2.4 GitHub — Source Code & Deployments

Both apps use auto-deployment — every push to the main branch on GitHub triggers a new deployment on Render automatically.

| GitHub account | nhaedutech (separate from school account) |
| --- | --- |
| Career Day repo | github.com/nhaedutech/STJ_career-spotlight-day (Private) |
| Sports Day repo | github.com/nhaedutech/STJ_sports-day (Private) |
| Landing page repo | github.com/nhaedutech/nhaedutech.github.io (Public) |
| Deploy trigger | Push to main branch |
| Deploy time | Approximately 2–4 minutes |

Always test changes locally before pushing to main. A broken push will take both the old and new version offline during the rebuild.

# 3. Pre-Event Operational Checklists

## 3.1 Career Spotlight Day — Before Registration Opens

| Task | Who | When | Done |
| --- | --- | --- | --- |
| Confirm app is live — visit careerday.nhaedutech.co.uk | NHA EduTech | 1 week before | ☐ |
| Export student data from Arbor MIS (Years 7, 8, 9, 10, 12) | Careers coordinator | 1 week before | ☐ |
| Import Arbor students via staff dashboard | Careers coordinator | 1 week before | ☐ |
| Import career sessions Excel file with rooms and capacities | Careers coordinator | 1 week before | ☐ |
| Verify student count matches Arbor export total | Careers coordinator | 1 week before | ☐ |
| Check all career sessions show correct capacity | Careers coordinator | 1 week before | ☐ |
| Share student sign-up URL with form tutors | Careers coordinator | Day before open | ☐ |
| Open registration from staff dashboard | Careers coordinator | Day registration opens | ☐ |
| Confirm registration shows as OPEN on homepage | Careers coordinator | Day registration opens | ☐ |
| Share tutor login URL and password with form tutors | Careers coordinator | Day registration opens | ☐ |

## 3.2 Career Spotlight Day — Before Allocation

| Task | Who | When | Done |
| --- | --- | --- | --- |
| Check dashboard — confirm acceptable sign-up percentage | Careers coordinator | Day before close | ☐ |
| Chase any forms with low sign-up via form tutors | Careers coordinator | Day before close | ☐ |
| Close registration from staff dashboard | Careers coordinator | Deadline day | ☐ |
| Download bookings CSV as backup before allocation | Careers coordinator | Before allocation | ☐ |
| Run allocation engine from staff dashboard | Careers coordinator | After closing | ☐ |
| Review allocation results — check unallocated students | Careers coordinator | After allocation | ☐ |
| Download PDF timetables per form group | Careers coordinator | After allocation | ☐ |
| Distribute timetables to form tutors | Careers coordinator | Before event day | ☐ |
| Download session registers for each room | Careers coordinator | Before event day | ☐ |

## 3.3 Sports Day — Before the Event

| Task | Who | When | Done |
| --- | --- | --- | --- |
| Confirm app is live — visit sportsday.nhaedutech.co.uk | NHA EduTech | 1 week before | ☐ |
| Upload student CSV via admin dashboard | PE coordinator | 1 week before | ☐ |
| Verify student count and house distribution | PE coordinator | 1 week before | ☐ |
| Check all events are seeded correctly | PE coordinator | 1 week before | ☐ |
| Share volunteer PIN with all volunteer teachers | PE coordinator | Day before | ☐ |
| Brief volunteers on result entry process | PE coordinator | Day before / morning | ☐ |
| Test volunteer login on a sample device | PE coordinator | Morning of event | ☐ |
| Open the leaderboard on a display screen | PE coordinator | Morning of event | ☐ |
| Confirm leaderboard auto-refreshes (check every 15 secs) | PE coordinator | Morning of event | ☐ |
| Enter 1–2 test results and confirm leaderboard updates | PE coordinator | Morning of event | ☐ |

# 4. On-the-Day Monitoring

## 4.1 What to Watch During Career Spotlight Day

- Check the staff dashboard periodically — confirm students are checking in to sessions

- Monitor the dashboard stats — Submitted Preferences count should be stable

- If a student reports they cannot find their session, check their booking in the dashboard

- If a session appears full unexpectedly, check availability CSV export

- Keep the Render logs tab open on a laptop during the event for instant error visibility

If the app becomes unresponsive during the event, first try a hard refresh (Ctrl+Shift+R). If that fails, check Render logs immediately and contact NHA EduTech.

## 4.2 What to Watch During Sports Day

- Monitor the leaderboard on the display screen — it should update every 15 seconds

- If the leaderboard stops updating, check volunteer devices are submitting results

- If a volunteer cannot log in, confirm they have the correct PIN

- If a result was entered incorrectly, the volunteer can delete it from their Enter Result screen

- Keep the admin login available for any urgent corrections

The leaderboard is public — students and parents can see it. Double-check results before submitting, especially relay race points which are doubled automatically.

# 5. Post-Event Checklists

## 5.1 Career Spotlight Day — After the Event

| Task | Who | When | Done |
| --- | --- | --- | --- |
| Download final bookings CSV as permanent record | Careers coordinator | Day after | ☐ |
| Close registration if still open | Careers coordinator | Day after | ☐ |
| Collect feedback from form tutors | Careers coordinator | Week after | ☐ |
| Send feedback to NHA EduTech for improvements | Careers coordinator | Week after | ☐ |
| Reset bookings from staff dashboard (keep MIS data) | Careers coordinator | End of year | ☐ |
| Confirm reset completed — dashboard shows 0 bookings | Careers coordinator | End of year | ☐ |

## 5.2 Sports Day — After the Event

| Task | Who | When | Done |
| --- | --- | --- | --- |
| Screenshot or download final leaderboard as record | PE coordinator | End of event | ☐ |
| Archive the year via admin dashboard (e.g. '2025-26') | PE coordinator | Day after | ☐ |
| Confirm archive saved — check Archive page | PE coordinator | Day after | ☐ |
| Reset live results via admin dashboard | PE coordinator | After archiving | ☐ |
| Run student rollover via admin dashboard | PE coordinator | Start of next year | ☐ |
| Upload new Year 7 students CSV | PE coordinator | Start of next year | ☐ |
| Collect feedback from volunteers | PE coordinator | Week after | ☐ |
| Send feedback to NHA EduTech for improvements | PE coordinator | Week after | ☐ |

# 6. Incident Response

If something goes wrong, use this table to identify the issue and respond correctly:

| Scenario | Action | Contact |
| --- | --- | --- |
| App won't load (504 timeout) | Wait 60 seconds and try again — free tier cold start. If persists after 2 minutes, check Render logs. | NHA EduTech if persists |
| App shows 500 error | Check Render logs immediately for the traceback. Note the error message and contact NHA EduTech. | NHA EduTech urgent |
| Staff cannot log in | Confirm correct password is being used. Check STAFF_PASSWORD env var on Render. Try clearing browser cookies. | NHA EduTech |
| Student username not found | Check username against Arbor export. Re-import Arbor data if needed. | Careers coordinator |
| Session shows wrong capacity | Re-import career sessions Excel with corrected capacity values. | Careers coordinator |
| Volunteer PIN rejected | Confirm correct PIN. Check VOLUNTEER_PIN env var on Render. | NHA EduTech |
| Leaderboard not updating | Hard refresh the page. Check volunteer is submitting results. Check Render logs for errors. | NHA EduTech if persists |
| Wrong result entered | Volunteer clicks undo/delete on their Enter Result screen. Admin can also delete from admin dashboard. | PE coordinator |
| App deployed broken code | On Render, go to Deploys tab and click Rollback to previous deploy. | NHA EduTech |
| UptimeRobot alert email received | Check Render logs immediately. If app is down, try manual redeploy from Render dashboard. | NHA EduTech urgent |
| Database connection error | Check DATABASE_URL env var on Render. For Sports Day, check Supabase is online at status.supabase.com. | NHA EduTech urgent |

For any urgent issue during a live event, email nexthorizon@nhaedutech.co.uk with URGENT in the subject line. Response target: within 30 minutes during school hours.

# 7. Maintenance Schedule

Recommended maintenance tasks to keep both systems healthy throughout the year:

| Frequency | Task | Who |
| --- | --- | --- |
| Weekly | Check UptimeRobot dashboard — confirm both monitors green | NHA EduTech |
| Monthly | Review Render logs for recurring errors or warnings | NHA EduTech |
| Monthly | Rotate GitHub Personal Access Token (expires every 90 days) | NHA EduTech |
| Termly | Confirm Namecheap domain auto-renew is on (nhaedutech.co.uk) | NHA EduTech |
| Annually | Update staff/tutor/volunteer passwords before each event | NHA EduTech + school coordinator |
| Annually | Review and update Privacy Policy if services change | NHA EduTech |

# 8. Contact & Escalation

| NHA EduTech email | nexthorizon@nhaedutech.co.uk |
| --- | --- |
| NHA EduTech website | nhaedutech.co.uk |
| Standard response time | Within 2 working days |
| Urgent response time | Within 30 minutes during school hours (email with URGENT in subject) |
| Render status page | status.render.com |
| Supabase status page | status.supabase.com |
| UptimeRobot dashboard | dashboard.uptimerobot.com |

NHA EduTech  ·  nhaedutech.co.uk  ·  nexthorizon@nhaedutech.co.uk  ·  © 2026 Next Horizon Achievements Ltd